## README
Construction cash-flow forecast — advance, retention, S-curve, fiscal years (Module 10, Lesson 6)
Yellow cells with blue bold text = INPUTS you may change.
Green cells = key RESULTS (formulas — do not overwrite).
WHAT THIS MODEL DOES
Turns a construction contract into a monthly payment forecast for the Employer (MEWRE) and a fiscal-year budget request. Gross work value comes either from an S-curve (cosine profile) or from a milestone payment schedule. From each interim payment certificate it deducts advance-payment recovery and retention, adds the advance at signature and the two retention releases, and sums net payments by fiscal year.
Default payment terms follow FIDIC 2017 conventions (advance recovered by amortisation starting when certified work exceeds 10% of the Accepted Contract Amount, at 25% of each IPC; retention at a percentage of each IPC up to a limit; half released at Taking-Over, half at the end of the Defects Notification Period). Your contract's Particular Conditions / Contract Data override these.
Fiscal year: Kuwait's state budget year is assumed to start in April (FY = 1 April to 31 March). This is widely reported but is NOT sourced in the course research brief — confirm with the Ministry of Finance budget circular. Change 'FY start month' if needed.
Sheets: Inputs -> Milestones (optional schedule) -> Monthly (months 0..48) -> FY Budget -> Contingency (commitment vs budget, contingency drawdown log).
EXERCISES
1. Base case (KWD 45.0 m, 24 months from June 2026, S-curve): confirm FY2026/27 net payments KWD 14.282 m, FY2027/28 KWD 26.755 m.
2. The contractor asks to raise the advance from 10% to 20%. What changes in FY2026/27 cash need and in MEWRE's exposure? What security must be increased?
3. Switch basis to milestones (Inputs basis = 2). Compare the FY split with the S-curve. Which is more realistic for a substation and OHL package?
4. A 3-month delay shifts the S-curve (set start date to Sep 2026). How much budget lapses from FY2026/27 and must be re-requested?
5. Contingency sheet: add a variation of KWD 0.8 m. What is the remaining contingency, and how would you explain the movement to the Audit Bureau?
DISCLAIMER
All numbers are ILLUSTRATIVE teaching values for a generic 1,100 MW PV IPP in Kuwait-like conditions. They are NOT the tariff, capex or terms of any real Shagaya / KAPP project (the Zone 1 tariff has not been published). Replace them with project data before using the model for any decision.
Currency convention: USD for IPP economics, KWD for ministry budgets; assumed 1 KWD = 3.25 USD (change in Inputs where shown).

## Inputs
Inputs — contract payment terms
Input | Value | Unit | Note / typical range
Accepted Contract Amount | 45 | KWD m
Month 0 (signature / advance date) | 2026-06-01 | date
Time for completion | 24 | months | Taking-Over assumed at month T
Advance payment | 10% | % of contract | Paid against an advance payment guarantee
Recovery starts when certified work exceeds | 10% | % of contract | FIDIC 2017 default 10%
Amortisation rate | 25% | % of each IPC | FIDIC 2017 default 25%
Retention rate | 10% | % of each IPC
Retention limit | 5% | % of contract
Defects Notification Period | 12 | months | Max 24 in this sheet
Gross value basis (1 = S-curve, 2 = milestones) | 1 | switch
Fiscal year start month | 4 | month (1–12) | Assumed April — verify

## Milestones
Milestone payment schedule (used when basis = 2)
Percentages must total 100%.
# | Milestone | % of contract | Month achieved | Value (KWD m)
1 | Approved route survey, design basis and SLD | 5% | 3
2 | Approved detailed design (towers, foundations, GIS layout) | 5% | 6
3 | Tower steel and conductor delivered to site (50%) | 10% | 9
4 | Foundations 50% complete | 10% | 10
5 | GIS and transformers factory acceptance tests passed | 10% | 12
6 | Tower steel and conductor delivered (100%) | 10% | 13
7 | Towers erected 100% | 10% | 16
8 | GIS and transformers delivered and installed | 15% | 18
9 | Stringing complete | 10% | 20
10 | Pre-commissioning and protection tests complete | 5% | 22
11 | Energization and Taking-Over | 10% | 24
Total (must be 100%)

## Monthly
Monthly payment forecast (KWD m) — formulas
Net payment = gross IPC + advance - advance recovery - retention + retention release.
Month | Date | Fiscal year | S-curve cum. % | Gross (S-curve) | Gross (milestones) | Gross IPC used | Cum. gross | Advance paid | Advance recovery | Retention held | Retention release | Net payment | Cum. net
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
Total
Formulas:
Date = EDATE('Inputs'!$B6,[Month])

## FY Budget
Fiscal-year budget request (KWD m)
SUMIF of the monthly forecast by fiscal-year label.
Fiscal year | Gross work certified | Advance paid | Advance recovered | Retention held | Retention released | Net cash payment (budget need) | Cumulative net
Check: total net = contract amount

## Contingency
Budget, commitment and contingency drawdown (KWD m)
Commitment = contract value + approved variations; expenditure = cash paid.
Input | Value | Unit | Note / typical range
Project contingency in approved budget | 4.5 | KWD m | 10% of contract; sized from the risk register (P80)
Owner's costs (consultant supervision, permits, MEWRE staff) | 2 | KWD m
Change / risk item | Status | Value | Probability | Expected value | Draws contingency?
VO-01 Additional tower foundation design for sabkha soil | Approved | 0.95 | 100%
VO-02 Extra 400 kV bay protection panel requested by MEWRE Transmission | Approved | 0.65 | 100%
Claim-01 Late site access (land handover by Employer) | Pending | 1.6 | 50%
Claim-02 Change in customs procedure (contractor claim) | Pending | 0.8 | 50%
Risk R-07 Outage window slippage on existing Al-Wafra substation | Risk (P80 allowance) | 2 | 40%
(add item)
(add item)
(add item)
Budget position | Value | Unit | How it is calculated
Approved budget = contract + contingency + owner's costs |  | KWD m
Contingency drawn (approved variations) |  | KWD m
Commitment = contract + approved variations |  | KWD m
Contingency remaining |  | KWD m
Expected value of pending claims and risks |  | KWD m
Contingency surplus (+) / shortfall (-) |  | KWD m | Negative = prepare a budget-increase justification
Forecast final cost (EAC) of the package |  | KWD m