## README
Earned value tracker — monthly (Module 10, Lesson 6; Module 8 EVM)
Yellow cells with blue bold text = INPUTS you may change.
Green cells = key RESULTS (formulas — do not overwrite).
WHAT THIS MODEL DOES
Tracks a contract or programme budget monthly with earned value management: PV (planned value), EV (earned value) and AC (actual cost) cumulative, and computes CV, SV, CPI, SPI, three EAC methods, ETC, VAC and TCPI. Example: a KWD 45.0 m grid-connection EPC package, 24 months, status at month 12.
Sheets: Inputs (BAC, status month) -> Monthly (enter planned % and cumulative EV and AC each month) -> Status (dashboard at the status month) -> Guidance.
Owner-side caution: on a lump-sum FIDIC contract MEWRE's cost is the Contract Price plus variations and claims, not the contractor's internal cost. Use AC = amounts certified (or accrued) for the Employer's view, and keep a separate forecast of variations and claims (see cashflow-forecast.xlsx, Contingency sheet).
EXERCISES
1. Read the Status sheet at month 12: CPI 0.934, SPI 0.880. Which EAC method would you report to the Undersecretary, and why?
2. Change the status month to 9. How have CPI and SPI trended? Is the trend or the point value more informative?
3. Enter your own EV and AC for months 13–15 assuming the contractor recovers (CPI 0.95, SPI 0.95). Recompute TCPI.
4. Plot PV, EV and AC (Insert > Line chart on Monthly columns C, E, F) and annotate CV and SV at the status date.
DISCLAIMER
All numbers are ILLUSTRATIVE teaching values for a generic 1,100 MW PV IPP in Kuwait-like conditions. They are NOT the tariff, capex or terms of any real Shagaya / KAPP project (the Zone 1 tariff has not been published). Replace them with project data before using the model for any decision.
Currency convention: USD for IPP economics, KWD for ministry budgets; assumed 1 KWD = 3.25 USD (change in Inputs where shown).

## Inputs
Inputs — EVM tracker
Input | Value | Unit | Note / typical range
Budget at completion (BAC) | 45 | KWD m
Status month | 12 | month no. | 1–24
Planned duration | 24 | months

## Monthly
Monthly EVM table
Enter planned cumulative %, EV cumulative and AC cumulative (yellow). Leave EV/AC blank for future months.
Month | Planned cum. % | PV cum. (KWD m) | EV cum. % complete | EV cum. (KWD m) | AC cum. (KWD m) | CV = EV-AC | SV = EV-PV | CPI = EV/AC | SPI = EV/PV | EAC1 = BAC/CPI | EAC2 = AC+(BAC-EV) | EAC3 = AC+(BAC-EV)/(CPI*SPI) | ETC = EAC1-AC | VAC = BAC-EAC1 | TCPI = (BAC-EV)/(BAC-AC)
1 | 0.43% |  |  | 0.191 | 0.192
2 | 1.7% |  |  | 0.751 | 0.759
3 | 3.81% |  |  | 1.661 | 1.689
4 | 6.7% |  |  | 2.894 | 2.959
5 | 10.33% |  |  | 4.417 | 4.542
6 | 14.64% |  |  | 6.195 | 6.407
7 | 19.56% |  |  | 8.187 | 8.515
8 | 25% |  |  | 10.35 | 10.827
9 | 30.87% |  |  | 12.64 | 13.299
10 | 37.06% |  |  | 15.009 | 15.883
11 | 43.47% |  |  | 17.411 | 18.533
12 | 50% |  |  | 19.8 | 21.2
13 | 56.53%
14 | 62.94%
15 | 69.13%
16 | 75%
17 | 80.44%
18 | 85.36%
19 | 89.67%
20 | 93.3%
21 | 96.19%
22 | 98.3%
23 | 99.57%
24 | 100%

## Status
Status at the selected month
Indicator | Value | Unit | How it is calculated
PV (planned value, cumulative) |  | KWD m
EV (earned value, cumulative) |  | KWD m
AC (actual cost, cumulative) |  | KWD m
Cost variance CV |  | KWD m | Negative = over cost for the work done
Schedule variance SV |  | KWD m | Negative = behind plan (in money terms)
CPI |  | – | <0.95 sustained = escalate
SPI |  | – | SPI tends to 1.0 at the end even if late — use time-based SPI(t) or the CPM schedule as well
EAC1 = BAC/CPI (typical) |  | KWD m
EAC2 = AC + (BAC-EV) (atypical, one-off) |  | KWD m
EAC3 = AC + (BAC-EV)/(CPI x SPI) (schedule pressure) |  | KWD m
TCPI (to complete within BAC) |  | – | >1.10 is rarely achieved in practice
Flag

## Guidance
GUIDANCE — reading EVM on a ministry project
1. PV comes from the baseline programme (resource-loaded P6 schedule or the payment S-curve). Freeze it at contract award; re-baseline only through formal change control.
2. EV must be measured, not estimated: use measured quantities x BoQ rates (remeasured contracts) or the agreed milestone/progress-weighting system (lump sum). Weighting rules belong in the contract's progress measurement procedure.
3. AC for the Employer = certified IPC value (plus owner's costs if tracking a programme). For a contractor, AC = its own cost; never mix the two bases in one CPI.
4. CPI < 0.95 or SPI < 0.95 for two consecutive months: ask for a recovery plan and update the cash-flow forecast and the budget request.
5. EAC choice: BAC/CPI when the cause is systemic (productivity, rates); AC + (BAC-EV) when the overrun was a one-off (e.g. a single repaired foundation); CPI x SPI when the client is forcing acceleration.
6. Report EAC with a range (best / most likely / worst) and connect it to contingency remaining. A single number invites false confidence.